## TFD magnet
WBS Category | Risk ID | Description | Mitigation | Impact | Rank | Status
Project management | R-PM-01 | Availability of resources and infrastructure: TFD competes with multiple programs and projects in BCMT, including 403b projects | Monthly meetings to review status/needs and update schedules for each area. Weekly meetings to plan specific tasks for engineering and technical resources. | Schedule delays due to infrastructure or resources being allocated to higher priority projects | H | Open
Project management | R-PM-02 | Scope redundancy included in project plan (extra coils, assembly and test cycles) insufficient to meet project goals | Ongoing discussions with DOE to assign contingency funds to the project; regularly monitor projected cost to completion based on updated status | Require additional funding or scope modifications in the later stages of the project | M | Open
Project management | R-PM-03 | Uncertainty in funding profile leading to delays in procurements or infrastructure availability | Received funding for the major procurement item (SC wire) and placed order. Main infrastructure upgrades are also completed or well underway. | Delay procurements of components for later coils | L | Open
Project management | R-PM-04 | Impact of covid pandemic on work controls and resource availability | Benefit from other projects experience working with covid restrictions | No significant impact on design phase; depending on future evolution, some possible impact on fabrication phase | L | Open
Facility Integration | R-FI-01 | Test conditions not yet finalized (e.g. geometry of sample holder, current/field orientation, temperature range for individual configurations) | Ongoing discussions with stakeholders (test facility team, users, HEP/FES offices, EOC) | Magnet/facility design may not be fully optimized to support testing program | H | Open
Facility Integration | R-FI-02 | Sample holder may need to be mechanically supported by magnet structure/bore | Performed analysis to assess the impact of forces from the sample holder to the bore on coil and structure | No significant impact based on analysis, but additional performance risks e.g. sample quench causing magnet quench | L | Open
Design and Analysis | R-DA-01 | Magnet field and bore size requirements translate in key parameters (e.g. coil stress) near or above established boundaries | Design optimization and conductor characterization show that all magnetic, mechanical and protection parameters are within established limits up to 16 T | Operating field will be based on feedback from magnet test and may be lower than 15 T target | L | Open
Design and Analysis | R-DA-02 | Complexity of engineering design requires more effort than anticipated | Closely following FRESCA2 design approach, and taking advantage of available experience at CEA/CERN | Increased cost and schedule delays | M | Open
Conductor and Cable | R-CC-01 | Wire performance: limited experience with the 162/169 layout selected for stability with large strand diameter (to limit cable aspect ratio) | Procurements by CERN (50 km) and TFD prototype (20 km) orders with identical design; detailed characterization of samples from both and formal review (WSR). | Reduced margin if Jc/RRR are found to be at the the lower end of the specs | L | Open
Conductor and Cable | R-CC-02 | Fail to procure wire that meets requirements at acceptable cost for the project | Production wire order has been placed: company is committed to deliver required quantities according to agreed upon specs and at fixed price | Significant impact if company fails to deliver on order, but probability is very low | L | Open
Conductor and Cable | R-CC-03 | Fabrication of long cable units: yield and/or quality is lower than expected | Prior to production cable runs: (1) parameter optimization, infrastructure upgrades, and long UL validation using copper/NbTi wire; (2) formally review results | Significant cost increase if additional cable ULs are required | H | Open
Braiding insulation | R-CF-01 | Braiding insulation issues | Prior to production runs: (1) perform braiding tests for parameter optimization; (2) define and agree upon vendor QC plan | Significant schedule impact if insulation defects require stripping and reapplying braiding. | L | Open
Coil Parts and Fabrication | R-CF-02 | Available coil fabrication infrastructure cannot adequately satisfy TFD requirements | Winding table upgraded for larger size/weight; new retort in procurement, new potting chamber harware/controls | Increased cost with respect to initial assumptions | L | Open
Coil Parts and Fabrication | R-CF-03 | Need to relocate equipment due to changing work space allocations | BCMT/LBNL management has identified space needs for TFD coil infrastructure and proactively relocated equipment | Moving long coil infrastructure (esp. reaction oven) would cause significant cost and schedule delay | L | Open
Coil Parts and Fabrication | R-CF-04 | Fail to select vendors to procure key coil components meeting specification and within acceptable cost and timeline | Preliminary drawings generated for all key coil components, requested quotes, identified at least one vendor that meets requirements | Procurement has not started: risk of significant price increases, schedule delays or insufficient quality of components | M | Open
Coil Parts and Fabrication | R-CF-05 | Availability of highly skilled technicians to successfully fabricate complex Nb3Sn coils | Continued effort to develop and cross-train technical team | Technician selection and training requires significant time and investment | H | Open
Coil Parts and Fabrication | R-CF-06 | Coil rejection rate is higher than anticipated | Prototype coil built to be usable in magnet; monitor coil production rate and take early action (e.g. additional conductor procurements) if needed | Significant impact on cost and schedule if additional spare coils need to be fabricated | M | Open
Coil Parts and Fabrication | R-CF-07 | Feedback from prototype coil leads to changes in component design or fabrication process | Delay procurement of components for later coils until prototype coil completion; adopt proven FRESCA2 solutions to minimize risk of significant revisions | Need to modify procured parts or procure additional parts | M | Open
Structure and Assembly | R-SA-01 | Implement pre-load for 15+ T operation while avoiding excessive coil stress and conductor damage | Plan includes a dummy coil assembly/cooldown to verify instrumentation and analysis predictions; and two assembly cycles to safely approach target preload | Additional cycles of assembly and test required | L | Open
Structure and Assembly | R-SA-02 | Insufficient training memory: magnet fails to recover quench level after a thermal cycle | This design demonstrated excellent training memory with FRESCA 2, with optimized preload. | Additional pre-load increase may be required to ensure sufficient memory | L | Open
Structure and Assembly | R-SA-03 | Fail to select vendors to procure key structure components meeting specification and within acceptable cost and timeline | Preliminary drawings generated for all key structure components, requested quotes, identified at least one vendor that meets requirements | Procurement has not started: risk of significant price increases, schedule delays or insufficient quality of components | M | Open
Magnet Qualification | R-MQ-01 | Damage in preparation for, or during, shipment of the magnet from LBNL to FNAL | Follow approach used for AUP shipments, including specially designed shipping crate, active accelerometer readings, and dedicated air-ride truck. | Damage to magnet would jeapardize whole project. | M | Open
Magnet Qualification | R-MQ-02 | Testing cost increase due to slow training | In case of slow training, test will be interrupted and a pre-load increase will be implemented | Increased risk of conductor damage due to higher preload | L | Open
Magnet Qualification | R-MQ-03 | LHe availability for magnet tests | Test dates will be agreed well in advance to ensure adequate planning and Fermilab has large storage capability | Test delay or higher cost | L | Open
Magnet Qualification | R-MQ-04 | Mechanical interactions magnet/facility | Shielding of magnet leak flux optimized for cost using a balance of cold iron yoke and warm shields outside cryostat. | Potential damage to test infrastructure due to magnet movement off-center | L | Open

## Test Facility
WBS Category | Risk ID | Title/Description | Mitigation | Impact | Rank (L/M/H) | Status
Project management | F-PM-01 | Escalation rate greater then predicted | Discussion with funding agency the increase of the contingency | Insufficient funds and delay the start of the test facility | H | open
Project management | F-PM-02 | Need to replace key personnel | Discussing the plans with the personnel and training the new employees as needed | Delay the start of the test facility | M | open
Project management | F-PM-03 | Availability of resources: TF competes with multiple programs and projects in APS-TD, including several 403b projects | Weekly meetings to discuss and plan specific tasks for engineering and technical resources. | Schedule delays due to infrastructure or resources being allocated to higher priority projects | H | open
Project management | F-PM-04 | Future Impact of the pandemic | Lab learned how to work in the pandemic environment. | Possible impact on engineering and technician work | L | open
Test facility construction | F-ME-01 | Increasing of the cost of civil construction due to the covid | Work with construction company to keep the schedule | Delay the start of the test facility | M | Closed
Test facility construction | F-ME-02 | Increasing of the cost of the civil construction due to the soil collapse | Using a special cylindrical support around the excavation | Delay the start of the test facility and cost increase | M | Closed
Cryostat procurement | F-CR-01 | Insufficient resources for top plate design due to conflict with other projects with higher priority | Discussing the plans with the personnel and training the new employees as needed | Possible impact on engineering design | L | Closed
Cryostat procurement | F-CR-02 | No bids for the cryostat production | Distributing the bid package and encourage company to bid | Delay the start of the test facility | M | Closed
Cryostat procurement | F-CR-03 | Problems with the Cryostat production | Weekly meetings with the vendor | Delay the start of the test facility | M | Open
Cryostat procurement | F-CR-04 | Material shortages | Discus with vendor on using alternative materials, SS304 instead of SS316 etc. | Delay for cryostat delivery and start of the test facility | M-H | Open
Cryostat procurement/TopPlate | F-CR-05 | Insufficient resources for top plate design due to conflict with other projects with higher priority | Discussing the plans with the personnel and training the new employees as needed | Possible impact on engineering design | L | Open
Cryostat procurement/TopPlate | F-CR-06 | No bid for top plate fabrication | Distributing the bid package and encourage company to bid | Delay the start of the test facility | M | Open
Cryostat procurement/TopPlate | F-CR-07 | Material shortages | Using alternative materials, SS304 instead of SS316 etc | Delay the start of the test facility | M-H | Open
Cryostat procurement/TopPlate | F-CR-08 | New code regulatory requirements | Discus and decide if lambda plate needs to be ASME code stamped and allocate sufficient funding | Delay the start of the test facility and cost increase | M-H | Open
QP/QM system | F-QP-01 | Operation flaw of the QP/QM system | The system is commissioned and tested on LHC AUP project and mu2e solenoids before to be used | Delay the start of the test facility and possible cost increase | L-M | Open
QP/QM system | F-QP-02 | Delay of the receiving the electronics part due to supply chain issues | Early ordering of the electronic components | Delay the start of the test facility | H | Open
Power Suppies Procurement | F-PS-01 | No bids for the PS production | Distributing the bid package and encourage company to bid | Delay the start of the test facility | M | Open
Power Suppies Procurement | F-PS-02 | Problems with the PS production | Weekly meetings with the vendor | Delay the start of the test facility | M | Open
Power Suppies Procurement | F-PS-03 | Fermilab's current control system does not work with the new power supplies | Work with the PS vendor and Fermilab PS group work out specifications | Delay the start of the test facility | L | Open
Facility integration | F-FI-01 | Not enough floor space to integrate all systems due to late project finish | Preparing a plan for space distribution in case that AUP does not finish in FY25 | Delay the start of the test facility and cost increase | H | Open
Facility integration | F-FI-02 | LHe availability for test facility integration due to the project or R&D urgent needs | Discuss the LHe distribution with the Cryo Department and projects | Test delay or higher cost | L | Open
Facility integration | F-FI-03 | Not enough tech support for mechanical and electrical due to conflict with other projects with higher priority | Discussing the plans with the personnel, employ and training the new employees | Delay the start of the test facility | M | Open