## Slide 1: ALICE USA Computing Project 2023 Tasklist
R. Jeff Porter (LBNL)
December 9th, 2022

## Slide 2: Our General To Do List – see PEAP
Evaluate new hardware purchases for 2023
  New CPU at both LBNL and ORNL
  New disk as needed and occupied
Attend Meetings
  EOS workshop at CERN, OSG All hands meetings, CHEP 2023
  Report operational status
    US Spring visit
    2023 T1/T2 workshop
Ongoing technical tasks
  IPv6 at ORNL
  Perfsonar at both sites & update OSG dashboard
  LHCOne at LBNL
Report to DOE
  Quarterly reports
  New AF Proposal
  FY2024 Update to PEAP

## Slide 3: US AF Prototype at LBL
Target systems: LBL legacy hardware
  Oldest 2 JBODS from current production EOS
  ~20+ 2015 PDSF Nodes (~640 cpu cores)
Configuration details:
  Drain and reconfigure old JBODS in current EOS
  Spin up new vobox + new ALICE LDAP entries
  Create new SLURM partition
Operational/Management Considerations:
  Irakli matrixed into HPCS group
    Can we spin up the ORNL Testbed for additional training or is that what is in rack 2?
  LHCOne for AF data feed? (maybe not prototype but future)
Priority & ETA:
  Moderately high
  April 2023

## Slide 4: Migrate LBL to whole-node scheduling
Target systems:
  Current LBL T2
Configuration details:
  Move STAR off of ALICE T2
    Copy data from STAR EOS into purchased file system on Lawrencium
    Request allocation on Lawrencium for STAR based on CPU procurements
  Modify SLURM and ALICE LDAP entries
Operational/Management Considerations:
  None?
Priority & ETA:
  High
  January 2023

## Slide 5: Migration to Perlmutter - baseline
Target system:
  NERSC/US supercomputers
Configuration details:
  Spin up New VOBox VM on HPCS system + ALICE LDAP entries
    Service run by “alicepro” account available to Sergiu/Irakli
  Integrate Superfacility API
    Test access by collaboration account
    Develop Token renewal service  push for 30 day lifetime
    Define R&D / logging structure (Give Maarten access!)
Operational/Management Considerations:
  None
Priority & ETA:
  Moderately high
  March 2023  End of CORI

## Slide 6: Migration to Perlmutter – extended
Target system:
  NERSC GPU resource
Configuration or R&D details:
  Confirm hand-build and run-ability on NVIDIA A100
  Optimize and test
  If workable, integrate build into ALICE Build system
Operational consideration:
  2nd Vobox for GPU partition?
Priority & ETA:
  Modest/low
  6-12 months

## Slide 7: US CCDB Repository
Target systems:
  US production EOS systems
Configuration details: details from CERN team
  Subdirectory definition: /something/
  Replication tag (expect 2 or 3 replicas/site)
Operational/Management Considerations:
  None?
Priority & ETA: LBL ASAP
  High
  January 2023

## Slide 8: ORNL Storage refresh
Target Systems:
  ORNL::EOS
Configuration details:
  Rack and configure new systems as ORNL::EOS with single disk FSID
    REL 8 or REL 9?
  Connect to legacy storage that still contain data as read-only
  Remove legacy storage once drained
Operational/Management Considerations
  Drain speed?
Priority & ETA:
  Moderately high
  February 2023

## Slide 9: CTF production resource at ORNL
Target Systems:
  legacy ORN::EOS
  ORNL T2
Configuration details:
  Configure CERN10 + 1 MGM w/ QuarkDb as new EOS storage
    EL 8 or EL 9?
    New name? ORNL::PRF
  Start copy of CTFs into new EOS storage
  Expand with old hardware as old ORNL::EOS is drained
Operational/Management Considerations
  None?
Priority & ETA:
  High
  December 2022?  likely January 2023

## Slide 10: ORNL CPU refresh
Target Systems:
  ORNL T2
Configuration details:
  Rack systems and run HEPSpec on new systems
    Cable as 10GigE
    Migrate to EL8 or EL9
  Evaluate amount of original hardware that can be retired
Operational/Management Considerations
  None
Priority & ETA:
  Moderately high to be used for CTF production
  January 2023

## Slide 11: Task tracking software
Target Systems:
  ALICE-USA computing project
Configuration details:
  Select tool that using Google Auth
Operational/Management Considerations
  None
Priority & ETA:
  high
  January 2023