## Slide 1: High Temperature Superconductor Cable Test Facility
Manufacturing and infrastructure status
José Luis Rudeiros Fernández, Diego Arbelaez, P. Ferracin, R. Hafalia, P. Mallon, M. Naus, S. Nguyen, R. Norris, G. Sabbi, A. Saravanan, M. Solis, G. Vallone
Lawrence Berkeley National Laboratory
March 20, 2024
LBNL, Berkeley, CA

## Slide 2: Outline
Introduction
Coil manufacturing
Magnet assembly
Summary

## Slide 3: Introduction
Presented coil fabrication process, main components, tooling, and fabrication sequence are focused on coil 1 (practice coil).
Components, fabrication tooling, and process expected to feedback into coil 2.
Coil fabrication
Preparation for winding
Winding
Preparation for reaction
Reaction
Preparation for impregnation
Impregnation
Magnet assembly
Half-shell yoke assembly
Alignment of two half-shell yoke assemblies
Coil pack insertion
Magnet loading
Coil 1
Coil 2
Magnet assembly processes to be tested during the dummy assembly (aluminum dummy coils).
Main contributions to all design presented here from the new design team: S. Nguyen, R. Norris, A. Saravanan

## Slide 4: Outline
Introduction
Coil manufacturing
Magnet assembly
Summary

## Slide 5: Coil manufacturing – Winding: support structure
Coil fabrication
Preparation for winding
New design of winding table (beam, lateral posts, and spool support).
Engineering Document in release process with all details of the upgraded winding structure.
Improved design of winding base components (reducing potential creep at high temperatures).
Upgraded winding support structure
Winding base design
B46
Progress since EOC #2

## Slide 6: Coil manufacturing – Winding: Pole and gaps
Coil fabrication
Preparation for winding
Table and pole spacing
Gaps for reaction
For the prototype coil, an initial gap in the pole will be established at >5 mm to ensure the gap does not close completely.
The material of the winding base (and all similar components) is planned to be a series 316 stainless steel.
Cable
Table center
Table extremity
Pole center
Pole extremity
Central plane
Initial estimations for gaps are based on information from CERN and LARP coils, as well as FRESCA2 coils.
B46
Exploration study comparing SS 316 and SS 400 series in order to find a better material for reaction tooling.
Implementation in the design of the winding base of required gaps.
Technical drawings in final release process.
Progress since EOC #2

## Slide 7: Coil manufacturing - Winding
Coil fabrication
Preparation for winding
Winding
During winding, the cable is held in place by a few that are pushed by a series of clamps that are locked into the outer groove included in the winding bases (like FRESCA2).
*No gaps are represented
Winding of the coil
Initial winding testing feedback into the design of the layer jump and winding process.
B46
B46
Redesigned clamping system and lateral pushers. First parts in fabrication.
Redesign of pole fillers for reaction.
Technical drawings in final release process.
Progress since EOC #2

## Slide 8: Coil manufacturing - Preparation for reaction
Coil fabrication
Preparation for winding
Winding
Preparation for reaction
After winding, the winding base is unlocked from the support structure, and the winding tension is relaxed.
The side rails (plasma sprayed in the inner surfaces) are put in place.
The side blocks are added until the coil is enclosed.
After placing the bore-filler the assembly is closed with a series of top plates.
The assembly is closed with bolted connections between the side pushers and base and top plates.
Double mica layer bridging the table gap.
B46
B46
B46
New design of reaction tooling components (significant reduction of complexity by reducing the number of components).
Improved design of reaction lead support, splice support, and end shoe pushers.
Progress since EOC #2

## Slide 9: Coil manufacturing - Reaction
Coil fabrication
Preparation for winding
Winding
Preparation for reaction
Reaction
Retort top
Gas
TCs main feedthroughs
Retort base
B46
B46
B46
B77A
Retort manufacturing
Commissioning of Reaction furnace in progress
The reaction furnace has been moved to its final work in B77A.
Extensive work has been carried regarding instrumentation and powering.
A series of tests leading to a full reaction cycle including retort and a dummy coil to fully qualify the system prior to the prototype coil are on-going.
In discussion with manufacturer
New retort high temperature sealing developed based on a flat mica gasket.
Improved design of retort based on a new developed high temperature sealing based on a flat mica gasket (instead of a round copper gasket).
Additional feedthroughs for measurement of gaps during reaction.
Retort fabrication drawings.
Completed testing after conclusion of work on instrumentation and electrical powering of the reaction furnace.
Progress since EOC #2

## Slide 10: Coil manufacturing - Preparation for impregnation
Coil fabrication
Preparation for winding
Winding
Preparation for reaction
Reaction
Preparation for impregnation
After the reaction, the top parts are removed, and the splicing process starts.
The current plan is to splice two NbTi cables to each Nb3Sn lead.
After the splice is completed, the transfer to the impregnation mold starts.
1
2
3
4
5
6
7
8
9
B46
B46
B46
B77A
B77A
Complete detail design step-by step of coil transfer from reaction to impregnation.
Progress since EOC #2

## Slide 11: Coil manufacturing - Impregnation
Coil fabrication
Preparation for winding
Winding
Preparation for reaction
Reaction
Preparation for impregnation
Impregnation
The impregnation mold is fixed to the impregnation chamber.
The magnet will be impregnated in an inclined position with CTD 101K.
New control, powering and heating system with 3 heating zones for maximum temperature uniformity during resin curing.
Commissioning of the impregnation system planned in the coming weeks.
B46
B46
B46
B77A
B77A
B77A
New control and power system
Impregnation mold for coil 1
Impregnation mold
Impregnation chamber commissioning
Adaptive filler pieces
The main filler pieces (i.e. the boat) are placed. The division of the fillers allows for the accommodation of small variations in the size of the coils after the reaction.
With the lateral plates, end plates, and top mold plates, a close cavity ready for impregnation is created.
The impregnation system is designed to accommodate slight variations in the size of the coils after the reaction.
Design of the impregnation mold.
Design and construction of the powering system of a 3-zone heating of the coil during impregnation.
Control system for the impregnation system.
Offline testing of the control system.
Electrical rewiring of the impregnation chamber completed.
Progress since EOC #2

## Slide 12: Outline
Introduction
Coil manufacturing
Magnet assembly
Summary

## Slide 13: Magnet assembly – Assembly space
Magnet assembly
B88
Total weight of approximately 18 tons
Designated space for assembly in B88 with available crane with sufficient capacity.

## Slide 14: Magnet assembly – Half-shell yoke assembly
Manipulation of the shell
The shell is designed as a pure cylinder with no features for 3D manipulation.
An exo-structure is placed around the shell to enable manipulation.
Assembly is picked up via hoist rings and moved to vertical position.
The half-shell is lowered around the yoke while it is is a collapsed position (closed yokes’ gap).
The yoke is opened with the help of a hydraulic cylinder and bladders.
Magnet assembly
Half-shell yoke assembly
Assembly
Vertical alignment of yoke and shell
1
2
3
B88

## Slide 15: Magnet assembly – Alignment of two half-shell yoke assemblies
Control of degrees of freedom of the half structures
The two half assemblies are aligned using a laser tracker.
The two parts are joined together through full length yoke rods and keys
Magnet assembly
Half-shell yoke assembly
Alignment of two half-shell yoke assemblies
B88
B88
Assembly
The combination of all positioning systems included allows for the control of 6 DOF of each half assembly.

## Slide 16: Magnet assembly – Coil pack insertion
Insertion
Magnet assembly
Half-shell yoke assembly
Alignment of two half-shell yoke assemblies
Coil pack insertion
B88
B88
B88
The coil pack is inserted with the help of a support table in horizontal position.
The coil pack is supported by rollers in flat cages.
After insertion, vertical bladders are used to elevate the assembly and remove the rollers.

## Slide 17: Magnet assembly – Magnet loading
Bladder system
Prototype bladders satisfactorily passed the tests.
Manufacturing of all bladders in progress.
Magnet assembly
Half-shell yoke assembly
Alignment of two half-shell yoke assemblies
Coil pack insertion
Magnet loading
B88
B88
B88
B88
End plate alignment
Axial loading
End plate
pusher
plate
piston
spacer plate
rod extension
The magnet is loaded axially with a hydraulic piston to a force of about 700 tons.

## Slide 18: Outline
Introduction
Coil manufacturing
Magnet assembly
Summary

## Slide 19: Summary
The design of the main tooling and manufacturing processes required for coil manufacturing are ready. Procurement of tooling has started.
Preparation of the required infrastructure for coil fabrication (i.e. reaction furnace and impregnation chamber) is on going.
The magnet assembly process is detailed in design, and procurement of required tooling has started.
Assembly space and compatible crane have been allocated to the project for the full magnet assembly.