## Slide 1
FRIB Nb3Sn ECR ion source magnet:
Schedule, Cost, and Progress monthly report
Tengming Shen for the Supercon team
Lawrence Berkeley National Laboratory
Jan 2025 report
2025/01/06
FRIB: Yoonhyuck Choi, Junwei Guo, Xiaoji Du, Dalu Zhang, Ting Xu, Guillaume Machicoane, Tomofumi Maruta, Jie Wei
LBNL: Tengming Shen, Ye Yang, Philip Mallon, Ray Hafalia, Lianrong Xi, Mariusz Juchno, Paolo Ferracin, Soren Prestemon
The Indico site where the meeting slides can be downloaded: https://conferences.lbl.gov/event/2032/
Access key: FRIB
Past meetings slides are available at https://conferences.lbl.gov/category/109/

## Slide 2: Progress since our last meeting, 2024/11/25
  Prototype coil fabrication.
    Coil winding completed.
    In preparation for reaction.
    An issue with the endshoes.
  Prototype coil cold test: Mirror magnet structure model assembly mechanical analysis, CAD model finalized, parts in production.

## Slide 3: Prototype coil winding completed
Prototype coil winding completed on 11/21/2024.

## Slide 4: Prototype coil winding completed
Prototype coil winding completed on 11/21/2024.
Return end
Lead end

## Slide 5: Prototype coil winding completed

## Slide 6: Coil being prepared for reaction
Issue – practical winding meets perfect endshoes.
          - Gap between endshoes and coil appears.
          - Grinding SS more difficult than grinding Aluminum.
Temporary solution: Add S-2 fiber glass.

## Slide 7: Explore potential long-term solutions
Develop 3D models of end shoes from survey data for better fit?

## Slide 8: Coil being prepared for reaction – leads region preparation
A critical region due to the brittleness of Nb3Sn after reaction.

## Slide 9: Splicing procedures being practiced and checked.
All parts for splicing have been fabricated.
Practice splicing technique and check soundness of parts, tooling,

## Slide 10: Mirror magnet mechanical model finalized
35mm
63.5mm
Ye Yang et al.

## Slide 11: Mirror magnet assembly procedure formulated
Apply the axial preload
  Pull the axial load and push the end plate 0.32mm x 2 in
Open the gap by the bladders
  Bladder pressure, 25MPa
Key insertion
  Key thickness, 175µm
Release the bladder pressure
Apply the final axial preload
  Pull the axial load and push the end plate 0.38mm x 2 in further
  Total interference between the nut and the end plate, 0.70mm x 2
Ye Yang et al.

## Slide 12: Loading assembly in production
    Shell, upper yoke and bottom yoke released for fabrication.
    SS end plates, pushers, spacers are released for fabrication.
    To be released for fab: 1) load pad, 2) axial rods, 3) key and shim assemblies.
Philip Mallon, Ryan Norris, Lianrong Xu et al.

## Slide 13: Goals next four weeks
    Complete preparation of prototype coil for heat treatment:
    Heat treatment of prototype coil.
    Complete mirror magnet assembly component fabrication.
      - Axial rods.
      - Load pad.
      - Key and shim assemblies.
    Initialize to outline tasks, estimate costs for the next phase, a full ECR magnet cold mass construction project.