## Slide 1
Steve Krave, FNAL
Tengming Shen, LBNL
10/31/2019
Insulation Systems and Technology R&D for FY20-22

## Slide 2: Charges from US MDP plan

## Slide 3: Tasks and goals
Tasks | Rationales | FY20 Q1/Q2 | FY20 Q3/Q4 | FY21 | FY22
1. Thermoplastics | Pros: High toughness and high radiation toughness Cons: (1) High viscosity and high processing temperature | Materials properties assessment: (1) CTE; (2) Shrinkage during cure. | Materials properties assessment: (3) Compression modulus and strength. (4) Shear strength. | Decision point: Testing Thermoplastics on CCT Nb3Sn subscale magnet (SM)? | 
2. High toughness resins with CTD | Investigate high toughness epoxy system besides NHMFL mix-61. Support small business to develop and verify new products. Supplement funding from SBIR. | Engage CTD materials testing |  |  | Decision point: Down selections and testing the best formulation on large size magnets. Radiation tests.
 |  | Cable and CCT mandrel fabrications | Testing CTD701x (not an epoxy) on CCT Nb3Sn SM |  | 
 |  |  |  | Testing second formulation on CCT Nb3Sn SM | 
 |  |  |  | Testing third formulation on CCT Nb3Sn SM | 

## Slide 4: Tasks and goals
Tasks | Rationales | FY20 Q1/Q2 | FY20 Q3/Q4 | FY21 | FY22
3. High specific heat, low CTE Gd2O3 nanoparticles filled epoxy | Stress management for epoxy, especially those neat resin areas between strands within Rutherford cables. | Ten turn 3D-printed CCT mandrel potting tests. | Decision point: Testing this approach on CCT Nb3Sn subscale magnet (SM)? |  | 
4. Understand epoxy failure with advanced diagnostics | Understanding characteristic events, feeding into modeling and machine learning models | Four cable stack short beam shear. S-2/fiber epoxy short beam shear. | S-2/fiber epoxy compression/shear |  | 
5. Improve epoxy resin and Nb3Sn QA/QC and processing controls | Understand impacts such as temperature gradient, shelf life, and moisture control etc. on properties of epoxy. | Effects of curing temperature on compression properties and Tg etc. | Effects of moisture control | Effects of shelf lives of epoxy components. | 
6. Nb3Sn Rutherford cable Insulation materials | What are alternative insulation systems and how will they affect quench training? |  |  |  | 

## Slide 5: Overview
Insulation Systems, Epoxies and Resins
  Targeting the interfaces that lead to training and limit magnet performance
    Understand Behavior
    Understand Variables
    Develop controls
Tooling and Coatings
  High Temperature compatible process developments
  Co-developed with sample fabrication
Off Project Work
  CTD SBIR
  AUP Studies and QC?

## Slide 6: Resins
Continue development of thermoplastic resins
  Re-design system for 8” ten stack system
  Test ULTEM, PEEK, HDPE
Demonstrate Low CTE Resin on Nb3Sn
  Improve adhesion to conductor
  Define behavior relationships
  Cable washing and etching
  Oxidizing/reducing reaction environment
(Re)Develop Further testing, processing, and QA/QC capabilities
  Fracture Toughness
  Robust CTE
  DSC
  FTIR
  Epoxy Handling equipment at MDTL

## Slide 7: Roadmap (FY 2020-2023)
2020 Q1/2 | 2020 Q3/4 | 2021 Q1/2 | 2021 Q3/4 | 2022 | 2023
Demonstrate Thermoplastic on Nb3Sn Cable
Demonstrate CTE Matched resin on Nb3Sn
Technology Subscale Fabrication-
Test
Interface Modification: Surface Treatments
Technology Subscale Fabrication-
Interface Modification Process changes
Test
Materials Evaluations
Technology Subscale Fabrication-
Test
Materials Evaluations
Technology Subscale Fabrication-
Test
Allow for continuous process improvement as understanding improves through magnet testing