## Slide 1
Stoyan Stoynev1, Emanuela Barzi1, Maxim Marchevsky2 , Xingchen Xu1
US Magnet Development Program
1Fermi National Accelerator Laboratory
2Lawrence Berkeley National Laboratory
Training Rate Enhancements
MDP Meeting
June 10, 2020

## Slide 2: Training Rate Enhancement Roadmap (as of February 2020)
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | High-Cp R&D
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Cable/stack training R&D
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | QCD R&D
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Vibrational R&D
2019
2020
2021
2022
2023
High-Cp applications
to coils
High-Cp wire concept development
Cable studies on
high-Cp wire
Q1 Q2 Q3 Q4
Q4
High-Cp cable
development and tests
Quench Current-boosting Device (QCD) development and tests on small models
QCD larger magnet
studies and tests
Ultrasonic pulsing
Vibrational tests development
Q1 Q2 Q3 Q4
Q1 Q2 Q3 Q4
Q1 Q2 Q3 Q4
Cable device and
sample development
Device fabrication and sample testing
CCT magnet tests
Strand and cable
FEM simulations
High-Cp wire and tape optimization

## Slide 3: Site access still limited
Most of the work severely affected by limited site access
Some work performed but remote possibilities exhausted
  High-Cp wire: no new update since the MDP/LTSW 2020
  High-Cp cable: No additional results since LTSW presentation
  QCD (Quench Current-boosting Device) designed, parts ordered, partial assembly, VMTF integration group created and plans approved; mirror magnet disassembled, parts assessed, work coordination and planning was on-going
  Ultrasonic pulsing plans on-hold due to overall magnet testing schedule rearrangements (still unknowns)

## Slide 4: QCD
Design finalized
Most of the hardware components ordered and received
(remaining some “interface” components)
Partial assembly
Simplified version
of the circuit
Some components of the QCD
were assembled but even partial
commissioning is still far away

## Slide 5: QCD (2)
One of four chokes that are needed to limit the di/dt in the switching devices of the QCD were assembled “in-house” (of technicians)
Both engineering (controls, wiring list, integration to existing infrastructure) and technical
(hardware ordering, technical drawings, actual work on components as some
technicians can work at home) aspects were covered.
Work on CONTROLS:
- figuring out the controls needed for the
QCD (experience with other devices; options).
- putting together a wiring list on how these boards would be
interconnected.
- Designing the PLC panel and ordering control power
components needed for the controls.
- Drawing for the overall controls diagram.

## Slide 6: QCD integration
The QCD will be integrated to the
CPS3 power system in IB1 at FNAL
CPS3 power area
QCD
VMTF
Control room area
Test Stand 4 (horizontal testing)
IB1 floor plan

## Slide 7: QCD integration (2)
Specification & Design Review
Procurement
Installation of Busbar/Diode assembly
Installation of other mechanical structures
Final Inspection & Testing
Documentation Review and Approval
Floor layout review
Mobilization
Floor installation
Updating floor layout drawing
Documentation Review and Approval
Safety documents including LOTO procedures
System integration test Procedures
Safety Interlock checkouts (triggered by PLC modification)
System Integration checkouts and tuning
ORC review and walkthrough
Project coordination within T&I
QCD impact to quench systems
QCD impact to power system hardware
QCD impact to safety systems
Specification, Design, & Review
PLC interface (ladder logic and iFix coding, wiring, testing)
ETS interface
Electrical power interface
QLM interface and modification (if necessary)
Summation Unit interface
Dump modification (if necessary)
Grounding modification (if necessary)
Procurement
Documentation Review and Approval
Plan created, each of the sub-tasks below has responsible identified,
coordination meetings held

## Slide 8: QCD - near term plans (to end of FY)
Preparatory integration work (that is, without the QCD itself) will be concluded
  This work is covered by Department support money
The rest of the work will likely* resume in the new FY
  Funding limits for the FY exhausted
  Engineers almost certainly busy with shut-down work throughout the Summer
* There is a chance we will be allowed to use money from next FY on credit