## Slide 1: FY21 Inventory
(Yes, even during a pandemic.)

## Slide 2: Inventory Base
The FY21 Statistical Sample Inventory will consist of:
100% of all assets with an Official Name of Computer-Laptop as of October 1, 2020
100% of all High Risk assets regardless of age
100% of all assets greater than $500,000 regardless of age
100% of assets currently on an authorized Loan, Mission-Related Personal Property Use Agreements (MPPUA), or Subcontract Agreement
100% of all custodians that are Invalid or have No Custodian as of 12/14/20

## Slide 3: Completion Timeline and Targets
Period # | Start Date | End date | Expected Completion %
1 | 1/4/2021 | 2/26/2021 | 75%
2 | 3/1/2021 | 4/30/2021 | 85%
3 | 5/3/2021 | 5/31/2021 | 95%
4 | 6/1/2021 | 6/30/2021 | 100%
Divisions failing to meet the expected completion percentage will follow the FY 21 Escalation Protocol and will be subject to the following:
Laboratory Senior Management notification
Division Senior Management notification and meeting
Progress meetings with Business Manager, ALD or Supervisor
OCFO Senior Leadership involvement
Ongoing Wall to Wall Inventories

## Slide 4: Big Fix Run Dates
Batch # | Date
1 | January 6, 2021
2 | January 20, 2021
3 | February 10, 2021
4 | February 24, 2021
5 | March 17, 2021
6 | April 14, 2021
7 | May 19, 2021

## Slide 5: Big Fix Inventory Technology