## Slide 1: Status and plans for the COMB magnet development
Vadim Kashikhin, Vito Lombardo
September 30, 2020

## Slide 2: COMB/REBCO development goals
The project objectives are twofold:
development of the novel Conductor on Molded Barrel (COMB) magnet technology and its initial demonstration (proof of principle) with an average-performance CORC® cable made of REBCO High Temperature Superconductor (HTS);
performance demonstration of the HTS accelerator magnet compatible with operation in a hybrid LTS/HTS magnet using the CORC® cable made of the state-of-the-art REBCO tapes (expected dipole self-field over 5 T) to meet the U.S. MDP goal (#2).
This technology, proposed at the beginning of 2019, is well suited for round conductors - including CORC® and STAR cables based on the latest generation of REBCO tapes and round Bi-2212 strands and cables. It offers an elegant solution for producing HTS inserts to boost the magnetic field strength in the superconducting accelerator magnets.

## Slide 3: Conductor On Molded Barrel (COMB) magnet technology
Magnetic field (T)
Equivalent stress (MPa)
Double-COMB
support structure
Mock-up coil built to demonstrate manufacturability
Nb3Sn coil
HTS coil
110 MPa
160 MPa
+1.25 T in Nb3Sn 4.4 T standalone
Within safe limits

## Slide 4: FY21 plans
The FY21 project goals are to design and fabricate one complete COMB dipole magnet (consisting of two half-coils, iron yoke and support structure) with the HTS CORC® conductor and test it in a standalone configuration at LN2 and LHe temperatures to demonstrate the proof of principle for the new technology with >4 T dipole field produced by the HTS cable in 100 mm bore. The next step is to re-assemble the HTS coils as an insert in the outer Nb­3Sn coils and structure from the 15-T dipole (with the cold test foreseen in FY22).
20 m of the CORC® cable for the first dipole magnet (two half-coils) has already been procured. Another 20 m of the high-performance CORC® (or STAR - TBD) cable will be needed in FY22 for the performance demonstration model (bore field >5 T). Given the long lead times on SuperPower REBCO tapes, the procurement should start soon.
FY21 milestones:
Stand-alone test of the COMB dipole magnet at LN2 temperature (expected bore field ~0.8 T).
Stand-alone test of the COMB dipole magnet at LHe temperature (expected bore field ~4.4 T).

## Slide 5: LN2 test setup
Short-term plans: use 2.5 m of CORC cable provided by LBL to assess the bending degradation.
  The wire was split into two pieces for redundancy.
  Each piece will be first tested in a large U-shape (~0.5 m bending diameter) to measure the undisturbed wire performance.
  Then ~2.5 turns will be wound into the pole groves of the COMB structure (~52 mm minimum bending diameter) and retested.
If the bending degradation is acceptable, we will proceed with the full magnet design and fabrication.
  Otherwise, the coil will have to be redesigned with a larger bending diameter (may no longer fit into the 123 mm bore of the available Nb3Sn magnet).
ORC is not required. Hazard Analysis is in progress. Testing starts in October.
LBL cable sample
Copper adapters and wire terminals provided by ACT

## Slide 6: Schedule