## Slide 1: We focused on c3 since last update in May 2021
We are ready to make the subscale c3
  3-turn version of c3 to practice and prepare for the full scale c3
  We have a plan on how to make it
Expect to start winding in November, if
  Receive conductors from ACT in September/October after addressing the lubricant issue [also see Vadim’s slides]
  Receive mandrels in November assuming funding will be available in October

## Slide 2: We have a plan on how to make the subscale C3
Wind with Winding Machine Mark #2
  First test with real conductor
Use Stycast to constrain the conductor and bond all the layers
  Stycast can flow through a radial gap of 0.010” or 254 µm

## Slide 3: Growing pain: challenges in the C3 order
SuperPower is able to meet the minimum Ic requirement that was specified for the first time
  350 A at 4.2 K, 6 T to provide margin to reach 5 T dipole field for c3
  ACT received 73% of total tape order
  67% of the received tapes meet the Ic spec
Some of the tapes that meet the Ic spec show weak mechanical performance
  Unexpected Ic degradation after winding into CORC®
Excellent opportunity to address these challenges now

## Slide 4: c3 needs in FY22
$200 k M&S, without overhead
  $35 k: conductors for the subscale c3
  $40 k: subscale c3 mandrels and other hardware
  $60 k: full-scale c3 mandrels
  $25 k: LHe to test sub- and full-scale c3
  $40 k: contingency
1.5 - 2 FTE effort to make and test the sub- and full-scale c3

## Slide 5: Backup slides

## Slide 6: Experiments show that we may use Stycast 2850 MT to fill the gap between c3 layers
Radial gap
0.020”
~ 0.010”
0.040”
It is necessary to fill the gap between c3 layers to reduce the stress on conductors at 5 T
CTD 528 can work
Test flow Stycast through a radial gap between the ID of an acrylic tube and the OD of an aluminum pipe
To be tested again with a pair of aluminum bronze tubes with the actual c3 radial gap of 0.0225” nominal

## Slide 7: Vacuum pressure impregnation needs more study
Collaboration with J. Stern and L. Chiesa from Tufts University and D. van der Laan and J. Weiss from ACT
We impregnated two sets of CORC® wires with FSU Mix-61 epoxy
Heating seems a common cause for the Ic degradation in both experiments with all four samples