## Slide 1
US Magnet Development Program
Training Reduction
MDP Meeting
November 10, 2021
Emanuela Barzi1, Maxim Marchevsky2 , Stoyan Stoynev1, Xingchen Xu1
US Magnet Development Program
1Fermi National Accelerator Laboratory
2Lawrence Berkeley National Laboratory

## Slide 2: Training reduction roadmap (as presented in 2020)
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | High-Cp R&D
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Cable/stack training R&D
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | QCD R&D
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Vibrational R&D
2019
2020
2021
2022
2023
High-Cp applications
to coils
High-Cp wire concept development
Cable studies on
high-Cp wire
Q1 Q2 Q3 Q4
Q4
High-Cp cable
development and tests
Quench Current-boosting Device (QCD) development and tests on small models
QCD larger magnet
studies and tests
Ultrasonic pulsing
Vibrational tests development
Q1 Q2 Q3 Q4
Q1 Q2 Q3 Q4
Q1 Q2 Q3 Q4
Cable device and
sample development
Device fabrication and sample testing
CCT magnet tests
Strand and cable
FEM simulations
High-Cp wire and tape optimization
In red border lines – independent funding

## Slide 3: Official training reduction roadmap
https://science.osti.gov/-/media/hep/pdf/Reports/2020/USMDP-2020-Plan-Update-web.pdf
Roadmap as in the official document:

## Slide 4: Milestones
QCD: Under completion, test expected in February 2021
High-Cp : Wire/cable tests performed with high-Cp
wrapped tape,
high-Cp wires with improved properties
fabricated, test with cables in 2022
FEM simulations in 2022
Ultrasonics: no SC magnet tests in FY21, we are
preparing for tests in FY22
Overall, we are running with 6-12 months delay due to
multiple factors.
Some studies may be hard to get to in a timely manner.
https://science.osti.gov/-/media/hep/pdf/Reports/2020/USMDP-2020-Plan-Update-web.pdf

## Slide 5: Future milestones
We may want to plan for a second “mirror”
magnet test first, as originally envisioned;
in any case FY22 is difficult for testing
Not expected till the end of 2022
It requires resources to develop and a
dedicated team, we could set up a team in FY22

## Slide 6: Spare